## Sheet1
On Site Visit Checklist
Task | Description
Validate Telco Data Lines | Look for and map out all inbound T1/PRI/ISDN lines to determine where they terminate. Get pictures for later reference.
Validate Current PBX | Look into the current PBX. If possible access the administrative interface to better determine call routing rules and assignments. Iook at used line cards and map out as best you can where cables are going.
Validate Analog Gateways | Are there analog gateways in use? These are typically 24 port devices with big old 50pin connectors in the back of them. If so, physically validate where they reside and try to get administrative access to them.
Validate ATA Devices | These are just small analog gateways with around 2-4 RJ9 ports. These are typically found behind all-in-one printers and fax machines.
Validate Phones | Get a count of the phones you will be replacing with VoIP phones. Determine if you will need to get any new cabling run to accommodate.
Validate Power | If you will be using a POE switch do you have enough POE capable ports to service the number of phones you will be deploying? If not, how many power or inline adapters will you need to purchase?
Validate Faxing | Faxing can be a touchy subject. Try to validate how many all-in-one printers actually have analog lines run to them for faxing. Some people assume that because a machine can fax that it is being used as a fax machine and this is not always the case.
How are emergency calls (911) handled? | Figure out any local requirements for emergency dialing.
Are there any current pain points? | Basically is anything in a known broken state?
Are there any known calling processes we should map out? | If there is a local support group, or other groups with special requirements it may be best to spend a little time with them to get a better understanding of their needs.
Is overhead paging in use? | If people dial special digits to connect and use overhead paging you should try to gather this information now so you can plan your dial plans accordingly.